## Blank Form
MDT Drilled Shaft Concrete Placement Log - Rev. Nov-12
Shaft Information
| Project Name | [5 empty] | Bent No.
| Project Number | [5 empty] | Shaft No.
| Contractor | [5 empty] | Station |  |  | See next tab for example
| Placement Date | [5 empty] | Offset
| Placement Method: |  | _______ | Freefall |  | Shaft Diameter:
|  |  | _______ | Gravity Tremie |  | Shaft Top Elevation:
|  |  | _______ | Pumped |  | Shaft Bottom Elevation:
| De-airing Method: |  | _______ | Relief Valve |  | Reference Elevation:
|  |  | _______ | Tremie Plug |  | Reference Description:
|  |  | _______ | Tremie Cap
|  |  | _______ | Other (Description)
Placement Log | [5 empty] | Determine after truck is empty:
| Truck No. | Concrete Volume | Arrival Time | Start Time | Finish Time | Depth to below reference to Tremie Orifice | Depth below reference to Concrete | Depth below reference to Water Surface in Shaft | Notes
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
Casing Removal | [5 empty] | Determine after moving:
| (Casing Adjustment #) |  | OD and length | Start Time | Finish Time | Bottom Elevation | Top Elevation | Notes
| Initial | [6 empty] | starting elevations
1
2
3
4
| Recorded by: |  |  |  |  | Date:

## Example Form
MDT Drilled Shaft Concrete Placement Log
Shaft Information
| Project Name |  | Bridge Project X |  |  |  | Bent No. | 1
| Project Number |  | Br 90-1(50)200 |  |  |  | Shaft No. | 1 (left shaft)
| Contractor |  | ACME Construction |  |  |  | Station | 110+15
| Placement Date |  | 2002-08-01 |  |  |  | Offset | 24' lt
| Placement Method: |  |  | Freefall |  | Shaft Diameter: |  |  | 6.6'
|  |  |  | Gravity Tremie |  | Shaft Top Elevation: |  |  | 3210.1
|  |  | x | Pumped |  | Shaft Bottom Elevation: |  |  | 3165.4
| De-airing Method: |  |  | Relief Valve |  | Reference Elevation: |  |  | 3215.21
|  |  | x | Tremie Plug |  | Reference Description: |  |  | Top of
|  |  |  | Tremie Cap |  |  |  | outer temp casing
Placement Log | [5 empty] | Determine after truck is empty:
| Truck No. | Concrete Volume | Arrival Time | Start Time | Finish Time | Depth to below reference to Tremie Orifice | Depth below reference to Concrete | Depth below reference to Water Surface in Shaft | Notes
1 | 31 | 10 | 8:00 | 8:10 | 8:25 | 54 | 42.11 | 25
2 | 16 | 10 | 8:00 | 8:30 | 8:40 | 54 | 34.41 | 17
3 | 55 | 10 | 8:30 | 9:15 | 9:35 | 45 | 26.71 | 8
4 | 21 | 9 | 9:45 | 9:50 | 10:20 | 35 | 19.71 | 0
5 | 18 | 9 | 10:20 | 10:25 | 10:50 | 35 | 12.71 | 0
6 | 31 | 10 | 11:30 | 11:35 | 12:00 | 20 | 5.1
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
Casing Removal | [5 empty] | Determine after moving:
| (Casing Adjustment #) |  | OD and length | Start Time | Finish Time | Bottom Elevation | Top Elevation | Notes
| Initial |  | 6.6' x 40' inner temp |  |  | 3175.4 | 3215.4 | starting elevations
| 1 |  | " | 9:35 | 9:45 | 3185.4 | 3225.4 | raised 10' after truck 3
| 2 |  | " | 12:00 | 12:35 |  |  | pulled remainder after truck 6
3
4
| Recorded by: |  |  | Joe Smith |  | Date: | 2002-08-01