## Activities
CONTRACT TIME CALCULATION
Preliminary Estimate
Project ID |  |  | UPN/Unit |  |  | Designer
Description |  |  | Length |  | mi. | Date
Type
Activity No. | Work Activity |  |  | Production |  | Duration |  | Preceding Activities
| Item | Quantity | Unit | Rate | Unit | Work | Other
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
Key Dates:
Comments:
Page 1

## Schedule
CONTRACT TIME CALCULATION
Preliminary Estimate
Project ID | [16 empty] | UPN/Unit | [8 empty] | Designer
Description | [16 empty] | Length |  |  |  |  | mi. |  |  |  | Date
Type
Act. No. | Pre.Act. | Day
|  |  | 5 |  | 10 | 15 |  | 20 |  |  | 30 |  |  | 40 |  | 50 |  |  | 60 |  | 70 |  | 80 |  | 90 |  | 100 | 110 | 120 |  | 130
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
|  | Working Days: | [6 empty] | * 1.1 = |  |  | 1.1
Use
Page 2
CONTRACT TIME CALCULATION
Preliminary Estimate
Project ID | [16 empty] | UPN/Unit | [8 empty] | Designer
Description | [16 empty] | Length |  |  |  |  | mi. |  |  |  | Date
Type
Act. No. | Pre.Act. | Day
|  |  |  | 140 |  |  | 150 |  |  | 160 |  |  | 170 |  | 180 |  |  | 190 |  | 200 |  | 210 |  | 220 |  |  | 230 | 240 | 250 |  | 260
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
Page 3

## Production Rates
Average Production Rates | [5 empty] | April 2008
|  |  | Metric Production |  | English Production
Work Activity |  | Type | Rate | Unit | Rate | Unit
Moblilization | Size method | Small (seal coat) | 2 | days min | 2 | days min
|  | Medium (< $2mil) | 5 | days | 5 | days
|  | Large (> $2mil) | 8 | days | 8 | days
|  | Extra Large (> $10mil) | 15 | days | 15 | days
BMP | Size method | Small (seal coat) | 2 | days | 2 | days
(or include in mob) |  | Medium (< $2mil) | 4 | days | 4 | days
|  | Large (> $2mil) | 6 | days | 6 | days
Earthwork | Topsoil | Small (shoulder work) | 600 | m3/day | 750 | yd3/day
(per vehicle) |  | Medium (or truck work) | 1500 | m3/day | 2000 | yd3/day
|  | Large (or scraper work) | 3000 | m3/day | 4000 | yd3/day
| Excavation | Small (shoulder work) | 1000 | m3/day | 1300 | yd3/day
|  | Medium (or truck work) | 3000 | m3/day | 4000 | yd3/day
|  | Large (or scraper work) | 4500 | m3/day | 6000 | yd3/day
| Borrow | Truck | 3000 | m3/day | 4000 | yd3/day
|  | Scraper | 4500 | m3/day | 6000 | yd3/day
| Rock - Blasting | Small | 500 | m3/day | 650 | yd3/day
|  | Large | 1500 | m3/day | 2000 | yd3/day
| Muck Exc. |  | 500 | m3/day | 650 | yd3/day
| Street Exc. |  | 500 | m3/day | 650 | yd3/day
Aggregate | Base Course | Small (tonnage) | 1800 | tons/day | 2000 | tons/day
|  | Medium (volume) | 2000 | m3/day | 2600 | yd3/day
|  | Large | 3000 | m3/day | 4000 | yd3/day
| Pulverization |  | 15000 | m2/day | 18000 | yd2/day
| CTB |  | 1000 | m3/day | 1300 | yd3/day
Drainage | Culverts | ≤ 18" | 90 | m/day | 300 | ft/day
|  | = 24" | 60 | m/day | 200 | ft/day
|  | > 24" | 45 | m/day | 150 | ft/day
|  | RCB | 10 | m/day | 30 | ft/day
| Storm Drain | Pipe (avg. depth, 6-8 ft; conventional backfill) | 100 | m/day | 330 | ft/day
|  | Manholes/Inlets | 4 | each/day | 4 | each/day
Plant Mix | Cold Milling | Mainline | 30000 | m2/day | 35000 | yd2/day
|  | Taper | 250 | m2/day | 300 | yd2/day
| Cold Recycle |  | 3 | lane km/day | 2 | lane mi/day
| PMS |  | 3000 | tons/day | 3300 | tons/day
| PMS Urban |  | 2000 | tons/day | 2200 | tons/day
| Seal & Cover |  | 12 | lane km/day | 7.5 | lane mi/day
| Rumble Strips |  | 8 | lane km/day | 5 | lane mi/day
Concrete Paving | PCCP | Uniform Width | 8300 | m2/day | 10000 | yd2/day
|  | Non-uniform Width | 1600 | m2/day | 2000 | yd2/day
| Repair | Grinding | 3000 | m2/day | 3500 | yd2/day
|  | Joint Sealing | 3000 | m/day | 10000 | ft/day
Pavement Markings | Epoxy | Small | 2 | days | 2 | days
|  | Large | 4 | days | 4 | days
|  | Words & Symbols | additional 1-2 | days | additional 1-2 | days
| Thermoplastic | Intersection | 3 | days | 3 | days
Miscellaneous | Curb & Gutter |  | 300 | m/day | 1000 | ft/day
| Sidewalk |  | 250 | m2/day | 300 | yd2/day
| Fencing | Woven wire/Barbwire | 300 | m/day | 1000 | ft/day
|  | Chain Link | 200 | m/day | 600 | ft/day
| Guardrail | Concrete | 365 | m/day | 1200 | ft/day
|  | Steel | 225 | m/day | 750 | ft/day
| Vegetation | Seeding | 5 | ha/day | 12 | acre/day
|  | Sodding | 3000 | m2/day | 3500 | yd2/day